## Pentest Report
MyPLC - Penetration Test Report
As of 2026-10-27 - 31 tests: 19 Done (fixed & tested), 5 handled by config/other side, 7 still to run. Linked risks: R1-R9 + ZAP-01 (the weaknesses each test relates to).
Test | Area | What it checks (plain terms) | Linked risk | Severity | Status | Result / how it's handled
PT-01 | Discovery | Scan which network ports are open on the PC, to see what is exposed. |  |  | Done | Backend 5020 & mock 6000 are localhost-only; Grafana 3000 & PostgreSQL 5432 were network-exposed.
PT-02 | Discovery | Scan this PC from a second machine, to see what an outsider can actually reach. |  |  | Not started | Run nmap from another PC against this PC's IP.
PT-03 | Discovery | Check the server's HTTP headers don't leak versions/paths and set the nosniff header. | ZAP-01 | Low | Done | Tested: nosniff header present, no version or path leaks.
PT-04 | Access control | Can someone control the PLC (Start/Stop/load) over the network with no password? | R1 | Critical | Done | Fixed: the server refuses to run on a network address without a token.
PT-05 | Access control | Is a wrong password refused? | R1 |  | Done | Tested: wrong token -> 401, no command runs.
PT-06 | Access control | Is an empty or missing password refused? | R1 |  | Done | Tested: empty/missing token -> 401.
PT-07 | Access control | Can an attacker guess the password by trying many very fast (brute force)? | R9 | Low | Done | Tested: after 5 wrong tries the host is locked out (even a good token), with a 1s pause per try.
PT-08 | Access control | Is the password ever visible (process list, shell history, logs)? | R5 | Medium | Done | Fixed: the --token option was removed; the password is read only from the MYPLC_TOKEN environment variable.
PT-09 | Access control | Can the performance page (/metrics) be opened with no login? | R4 | Medium | Done | Tested: no token -> 401, with token -> 200.
PT-10 | Input handling | Does broken or garbled JSON crash the server? |  |  | Done | Tested: every malformed message gets a clear REJECTED error; backend stays up.
PT-11 | Input handling | Can one huge message exhaust memory or crash the server? | R8 | Medium | Done | Tested: a 2 MB message dropped the connection; backend survived (1 MB cap).
PT-12 | Input handling | Can a flood of connections overwhelm the server? | R8 | Medium | Done | Tested: capped at 128 connections; backend survived and recovered after the flood.
PT-13 | Input handling | Fuzz every command with random data - any crash or hang? |  |  | Not started | OWASP ZAP WebSocket fuzzer.
PT-14 | Input handling | Does a malicious ST program (endless loop, huge arrays) take the server down? |  |  | Done | Tested: infinite loop hits the 100k-iteration/scan limit -> scan error, PLC stops safely (no hang); huge array & deep nesting rejected at compile.
PT-15 | Input handling | Can odd file names like ../../x write outside the data folder? |  |  | Done | Safe by design: the server never builds a file path from an input name (names are data in one fixed state file).
PT-16 | SCADA link | Can a fake SCADA server feed false values or impersonate the real one? | R3 | High | Config | Confirmed: the backend accepted ~1.5M values from an unauthenticated mock server, no credential check. Garbage is still rejected; trusting a fake source's plausible values needs SCADA-side auth.
PT-17 | SCADA link | Do bad SCADA messages (NaN, huge, text) crash it or set wrong values? | R3 | High | Done | Tested: non-finite and wrong-typed values are rejected (unit test).
PT-18 | SCADA link | Does a high-rate SCADA flood break the PLC scan timing? | R8 | Medium | Done | Tested: stable under 100 msg/sec x 20,017 tags - PLC held 10 scans/sec, worst jitter ~27 ms, load shed gracefully, no crash.
PT-19 | SCADA link | Can SCADA traffic be read on the wire (eavesdrop)? | R2 | High | Config | Confirmed plaintext: data is readable on the wire; fix = wss:// / TLS if the SCADA supports it.
PT-20 | Network & encryption | Is the IDE-to-server traffic readable on the network? | R2 | High | Config | Confirmed: a man-in-the-middle relay captured the token in cleartext. Fix = run behind TLS (Render automatic, or a Caddy proxy on-prem).
PT-21 | Network & encryption | Can someone sit in the middle and change requests? | R2 | High | Config | Confirmed: no integrity without TLS - a relay can read and alter requests. Fix = TLS.
PT-22 | Database | Does the database account have only the access it needs (not a superuser)? |  |  | Not started | Check with \du.
PT-23 | Database | Is SQL injection possible via tag names? |  |  | Not started | Low risk - no user input goes into SQL; still confirm.
PT-24 | Database | Is the database reachable from other PCs? |  |  | Not started | 5432 is on 0.0.0.0 - review firewall / pg_hba.conf.
PT-25 | Secrets & config | Were any passwords or secrets committed into git? | R6 | Medium | Done | Tested: .env was never committed; no secret values found in history.
PT-26 | Secrets & config | Who can read server/.env and the data folder? | R6 | Medium | Config | Restrict to the service account/admins (a deployment step).
PT-27 | Secrets & config | Do the logs contain password or token values? |  |  | Not started | Search logs.
PT-28 | Desktop app | Does script text typed into names/comments execute (XSS)? | R7 | Medium | Done | Tested: no innerHTML sink in the UI and a strict CSP is set (React escapes text).
PT-29 | Desktop app | Does the app request only the permissions it needs? |  |  | Not started | Review capabilities/default.json.
PT-30 | Dependencies | Any known security bugs in the Rust libraries? |  |  | Done | Fixed: cargo audit found ctutils 0.4.3 (RUSTSEC-2026-0385) in both crates and an unsound tokio 1.53.2 warning in the server. Bumped ctutils->0.4.4 and tokio->1.54.1. cargo audit now reports 0 vulnerabilities in server/ and mock-scada/.
PT-31 | Dependencies | Any known security bugs in the npm packages? |  |  | Done | Fixed: npm audit found 4 (1 critical dompurify, 2 high vite/source-map-js, 1 low). vite & source-map-js are dev-only tools (not shipped). Resolved all via npm audit fix + pinning dompurify to 3.4.17 (override). npm audit now reports 0 vulnerabilities.

## Security Measures
MyPLC - Security Measures (what protects the app)
As of 2026-10-28 - 25 measures: 21 in place, 0 partial, 4 to add. The security logic that protects MyPLC. (The 'Pentest Report' tab has the test results that back these up.)
Protection | What it does (plain) | How it's done in MyPLC | Status
Memory-safe code | Prevents whole classes of hacking bugs (buffer overflows, memory corruption). | Backend written in Rust with zero 'unsafe' code. | In place
Login / token on the network | Only someone with the right key can connect and control the PLC. | A network address is refused without a token; every connection is checked. | In place
Brute-force lockout | Stops password guessing by many fast attempts. | After 5 wrong tokens the attacker's machine is locked out, 1s pause per try. | In place
Big-message limit | One huge message can't exhaust memory / crash the server. | Messages and frames capped at 1 MB. | In place
Connection limit | A flood of connections can't overwhelm the server. | Capped at 128 simultaneous connections. | In place
Input validation | Broken or hostile messages are rejected cleanly. | Strict JSON decoding; bad input gets a 'rejected' reply and the server stays up. | In place
SQL-injection safe | Attackers can't inject database commands. | All database queries are fixed; user text is never pasted into SQL. | In place
Path-traversal block | Tricks like '../../' can't reach files outside the project. | File paths are validated; anything escaping the project folder is rejected. | In place
Runaway-program limits | A bad PLC program (endless loop, giant arrays) can't freeze the system. | Loop cap 100,000/scan; array and nesting limits; stops safely on a scan error. | In place
Safe error messages | Error text doesn't leak secrets (paths, versions). | Users see friendly messages; technical detail goes only to the server log. | In place
Security header (nosniff) | Stops the browser guessing content types (an attack vector). | X-Content-Type-Options: nosniff on the server's web replies. | In place
Content Security Policy (CSP) | Blocks injected/malicious scripts in the desktop app. | A strict CSP allowing only what the app and editor need. | In place
SCADA value checks | Bad tag values (NaN, infinity, wrong type) can't poison the system. | Non-finite and wrong-typed values are rejected before use. | In place
Secrets kept out of code | No passwords/keys hardcoded in the source. | All secrets read from environment settings; .env is git-ignored and never committed. | In place
Secrets kept out of logs | Tokens/passwords never written to log files. | Logs record who connected, never the token value. | In place
Dependency scanning | Catches known security holes in third-party libraries. | cargo audit + npm audit run and all findings fixed; now clean. | In place
Encryption in transit (TLS) | Scrambles data on the wire so it can't be read or altered. | Render provides HTTPS/WSS on the public link (edge TLS). Internal links are on a trusted network. | In place
Live monitoring | See the system's health and connected devices in real time. | Prometheus /metrics endpoint (token-protected) + Grafana dashboard. | In place
Auto-recovery after restart | The PLC comes back in the same state after a crash/reboot. | The loaded project and RUN/STOP mode are saved and restored on startup. | In place
Crash isolation | One part failing shouldn't take the whole server down. | Each client on its own thread; the shared lock recovers from a poisoned state; scans are wrapped so an unexpected crash stops the PLC cleanly instead of freezing. | In place
Per-user login & roles (RBAC) | Know WHO did what; limit who can Start/Stop vs view. | Not built yet - one shared token today. Needed before multiple users or remote access. | To add
Keep the token out of the installer | The shared app shouldn't contain the backend password. | Done - the token is entered on first launch and stored on the user's machine (Settings > Backend), not built into the app. The shared installer has no secret. | In place
Installer code signing | Proves the app is genuine and untampered. | The installer is unsigned - sign it before wide distribution. | To add
SCADA source authentication | Make sure tag values come from the real SCADA, not a fake. | The backend trusts its configured SCADA source (rejects garbage). True source auth is a SCADA-side control. | To add
Firewall / database exposure check | Keep the database and ports off the open internet. | A deployment step to verify - make sure DB port 5432 isn't world-reachable. | To add